## Sheet 1
BID TABULATION - Wednesday, March 26, 2014 - HIGHWAY CONSTRUCTION Allegan County Road Commission 1308 Lincoln Road Allegan, Michigan 49010-9762 |  |  |  | PROJECT NO. 4735 – 1.00 miles of roadway reconstruction including grade establishment, sand subbase, aggregate base, culvert replacements, and restoration on 108th Street from 2nd Street to Patterson Road, Leighton Township, Allegan County.
PRELIMINARY
ENGINEER'S ESTIMATE
|  |  | UNIT |  | UNIT |  | UNIT |  | UNIT
ITEM OF WORK | QUANTITY | UNIT | PRICE BID | AMOUNT | PRICE BID | AMOUNT | PRICE BID | AMOUNT | PRICE BID | AMOUNT
Clearing | 1 | LS |  | 0 |  | 0 |  | 0 | 50000 | 50000
Station Grading | 1 | LS |  | 0 |  | 0 |  | 0 | 45000 | 45000
Subbase, CIP | 7730 | Cyd |  | 0 |  | 0 |  | 0 | 5.5 | 42515
Topsoil Surface, Salv, LM | 2000 | Cyd |  | 0 |  | 0 |  | 0 | 3 | 6000
Geotextile, Stabilization | 7000 | Syd |  | 0 |  | 0 |  | 0 | 2 | 14000
Aggregate, 6A | 50 | Ton |  | 0 |  | 0 |  | 0 | 17 | 850
Subgrade Undercutting, Type II | 4000 | Cyd |  | 0 |  | 0 |  | 0 | 7 | 28000
Culv, Cl F, 12 inch | 340 | Ft |  | 0 |  | 0 |  | 0 | 12 | 4080
Culv, Cl F, 18 inch | 180 | Ft |  | 0 |  | 0 |  | 0 | 16 | 2880
Culv, Cl E, Conc, 18 inch | 176 | Ft |  | 0 |  | 0 |  | 0 | 30 | 5280
Culv End Sect, Conc, 18 inch | 8 | Ea |  | 0 |  | 0 |  | 0 | 500 | 4000
Underdrain, Subgrade, 6 inch | 1000 | Ft |  | 0 |  | 0 |  | 0 | 2.75 | 2750
Underdrain Outlet, 6 inch | 40 | Ft |  | 0 |  | 0 |  | 0 | 6 | 240
Underdrain, Outlet Ending, 6 inch | 4 | Ea |  | 0 |  | 0 |  | 0 | 125 | 500
Approach, Cl II | 230 | Ton |  | 0 |  | 0 |  | 0 | 12 | 2760
Approach, 21AA | 50 | Ton |  | 0 |  | 0 |  | 0 | 15 | 750
Aggregate Base, 6 inch | 18900 | Syd |  | 0 |  | 0 |  | 0 | 3 | 56700
Restoration | 1 | LS |  | 0 |  | 0 |  | 0 | 5000 | 5000
Extended Restoration | 1 | LS |  | 0 |  | 0 |  | 0 | 1000 | 1000
Seeding, Mixture CR | 300 | Lbs |  | 0 |  | 0 |  | 0 | 2 | 600
Sign, Type B, Temp, Modified | 143 | Sft |  | 0 |  | 0 |  | 0 | 5 | 715
Plastic Drum, High Intensity, Lighted Modified | 30 | Ea |  | 0 |  | 0 |  | 0 | 20 | 600
Barricade Type III, High Intensity, Dbl Sided, Ltd, Mod. | 2 | Ea |  | 0 |  | 0 |  | 0 | 150 | 300
Riprap, Plain | 60 | Syd |  | 0 |  | 0 |  | 0 | 40 | 2400
Mulch Blanket | 1300 | Syd |  | 0 |  | 0 |  | 0 | 1.25 | 1625
Mulch Blanket, High Velocity | 2800 | Syd |  | 0 |  | 0 |  | 0 | 1.5 | 4200
Erosion Control, Silt Fence | 500 | Ft |  | 0 |  | 0 |  | 0 | 2 | 1000
Erosion Control, Check Dam | 100 | Ft |  | 0 |  | 0 |  | 0 | 15 | 1500
Project Cleanup | 1 | LS |  | 0 |  | 0 |  | 0 | 1500 | 1500
|  |  | TOTAL BID | 0 | TOTAL BID | 0 | TOTAL BID | 0 | TOTAL BID | 286745